## Project Estimate - Summary
PROJECT INFORMATION
OWNER:
ADDRESS: | 725 Santa Fe
DESCRIPTION: | 56 Unit Condos
ESTIMATOR: | Douglas Kopel
ARCHITECT: | Studio Completiva
DESIGNER: | Denver Design Build
DATE: | 8/20/2019 FINAL GMP
DIRECT COST
CSI DIVISION |  | COST | % of Cost
01 - General Requirements |  | 2206357 | 12.16%
02 - Site Construction |  | 1070706.5098 | 5.899%
03 - Concrete |  | 6441663.15 | 35.49%
04 - Masonry |  | 0 | 0%
05 - Metals |  | 352875 | 1.944%
06 - Wood & Plastics |  | 127968.25 | 0.7051%
07 - Thermal & Moisture Protection |  | 742034.55 | 4.088%
08 - Doors & Windows |  | 327130.52 | 1.802%
09 - Finishes |  | 2616722.0625 | 14.42%
10 - Specialties |  | 79264.11 | 0.4367%
11 - Equipment |  | 159600 | 0.8793%
12 - Furnishings |  | 0 | 0%
13 - Specialty Construction |  | 484248.1 | 2.668%
14 - Conveying Systems |  | 336050 | 1.852%
15 - Mechanical |  | 1806563.42 | 9.954%
16 - Electrical |  | 1398698.78 | 7.706%
DIRECT COST - SUMMARY |  | 18149881.4522 | 100%
CONTRACTING REQUIREMENTS
CSI DIVISION |  | COST | NOTES
Column1 | Column2 | Column3 | Column4
00-100 ¦ Permit & Plan Review Fees |  | 0 | By Owner
00-100 ¦ Use Tax |  | 0 | Excluded
00-100 ¦ Tap Fees |  | 0 | Excluded
00-100 ¦ Xcel Fees |  | 0 | By Owner
00-150 ¦ General Liability Insurance - Professional (OCIP) Required |  | 0 | By Owner
00-150 ¦ General Liability Insurance - Construction (OCIP) Required |  | 0 | By Owner
00-150 ¦ Builders Risk Insurance |  | 0 | By Owner
00-200 ¦ Legel Fees - DDB |  | 0 | Included
00-300 ¦ Project Design/Build Construction Contingency |  | 680620.5545 | 3.75%
00-400 ¦ Contractor Overhead |  | 362997.629 | 2%
00-400 ¦ Contractor Fee |  | 362997.629 | 2%
00-500 ¦ Marketing |  | 0 | N/A
CONTRACTING REQUIREMENTS - SUBTOTAL |  | 1406615.8125
TOTAL - PROJECT |  | 19556497.2648
PLEASE NOTE
1. This estimate is good for 30 days
2. If a construction contingency is not included in this estimate, it is recommended to include one.

## Project Estimate - Detail
PROJECT INFORMATION
| OWNER: |  |  |  |  | SQUARE FOOTAGE - Sale/Lease |  | 54423
| ADDRESS: | 725 Santa Fe |  |  |  | SQUARE FOOTAGE - Gross |  | 91780
| DESCRIPTION: | 56 Unit Condos |  |  |  | COST PER SF - Sale/Lease |  | 265.753
| ESTIMATOR: | Douglas Kopel |  |  |  | COST PER SF - Gross |  | 213.0802
| ARCHITECT: | Studio Completiva |  |  |  | PROJECT DURATION (ESTIMATED): |  | 52 Weeks
| DESIGN TEAM: | EES Civil Engineering |  |  |  | Apartment/Units SF Retail |  | 45638
|  | Monroe Newell/Erciksen Roed Structural Engineering |  |  |  | Retail/Units SF |  | 8785
|  | Canyon/JCAA Plumbng Engineering |  |  |  | Lobby SF |  | 0
|  | Marxaire/JCCA HVAC Engineering, Hi-Tech/Rossie Electrical Engineering EDI Sound Engineering |  |  |  | Utility/Cores SF |  | 13624
|  | Hi-Tech/Rossie Electrical Engineering |  |  |  | Amenity Space SF |  | 5542
|  | EDI Sound Engineering |  |  |  | On Grade Parking SF |  | 0
| DATE: | 2019-08-20 |  |  | FINAL GMP | Underground Parking SF |  | 18191
DIRECT COSTS - CONSTRUCTION
01 - General Requirements
# | DESCRIPTION | QTY | UNIT | UNIT PRICE | COST | COMMENTS | COST CODE | TYPE
1 | MANAGEMENT/LABOR
2 | Project manager | 60 | WK | 3680 | 220800 | DDB
3 | Lead superintendent 1 | 60 | WK | 3000 | 180000 | DDB
4 | Lead superintendent 2 | 30 | WK | 3000 | 90000 | DDB
5 | Assistant superintendent 1 | 30 | WK | 2400 | 72000 | DDB
6 | Project engineer 1 | 60 | WK | 2400 | 144000 | DDB
7 | Accounting & billing labor | 14 | MO | 1000 | 14000 | DDB
8 | Procore management software |  |  |  | 0 | Included - In Overhead
1 | INSPECTIONS/ WARRANTY/SURVEY
2 | Structural engineering inspections - Soils | 15 | EA | 750 | 11250 | RMG
3 | Structural engineering inspections - Welding | 15 | EA | 750 | 11250 | RMG
4 | Concrete compaction & slump testing | 15 | DY | 750 | 11250 | RMG
5 | Structural engineering inspections - Soils | 1 | LS | 34300 | 34300 | RMG - Denver Water Maim Replacement
6 | Private storm and water special inspections |  |  |  | 0 | Excluded
7 | Surveying - Construction | 1 | LS | 18500 | 18500 | Powers Surveying
8 | As-builts | 1 | LS | 0 | 0 | EES - Included
9 | Warranty service | 1 | LS | 0 | 0 | Excluded, by Owner
1 | OTHER GENERAL REQUIREMENTS
2 | General materials | 14 | MO | 1250 | 17500 | DDB
3 | Small tools and consumables | 14 | MO | 500 | 7000 | DDB
4 | Finishes protection | 45638 | SF | 0.75 | 34228.5 | DDB
5 | Sanitary facilities | 14 | MO | 550 | 7700 | DDB
6 | Winter condo, weather protect, rain, snow removal, temp heat | 1 | EA | 15000 | 15000 | Allowance
7 | Site security - cameras, locks, lighting, misc. | 14 | MO | 750 | 10500 | DDB
8 | Internet service and cell phone | 14 | MO | 400 | 5600 | DDB
9 | Temporary water & power billings | 14 | MO | 1000 | 14000 | DDB
10 | Safety supplies, meetings, training & inspections | 14 | MO | 350 | 4900 | DDB
11 | Jobsite office supplies, blueprints, printing & site drinking water | 14 | MO | 350 | 4900 | DDB
12 | Blower door testing | 1 | FL | 10000 | 10000 | Scott Enviromental
13 | Final & window cleaning | 45638 | LS | 0.75 | 34228.5 | SNR Contractors
14 | Mileage | 14 | MO | 275 | 3850 | DDB
1 | TEMPORARY EQUIPMENT
2 | Temp fencing and signage | 14 | MO | 1250 | 17500 | DDB
3 | Temp concrete barriers - Shoring wall | 6 | MO | 5500 | 33000 | DDB
4 | Mobile office 8'x20' | 14 | MO | 1250 | 17500 | DDB
5 | Storage containers | 14 | MO | 450 | 6300 | DDB
6 | Boom lifts | 4 | MO | 8000 | 32000 | DDB
7 | Fork lifts | 4 | MO | 8000 | 32000 | DDB
8 | Hoisting equipment
9 | Cranes - tower 1 | 3 | MO | 40700 | 122100 | Wells Concrete - RMS Cranes W/ Operator
10 | Cranes - tower 1 | 1 | LS | 125000 | 125000 | Wells Concrete - RMS Cranes - In/out
11 | Temporary - Covered Sidewalk | 100 | LF | 175 | 17500 | DDB
12 | Construction trash chute | 8 | MO | 2500 | 20000 | DDB
1 | ARCHITECTURE/ENGINEERING/DESIGN |  |  |  | 0
2 | Peer review - CODE ONLY | 1 | LS | 10880 | 10880 | Masoud
3 | Architecture | 1 | LS | 375000 | 375000 | Studio Completive
4 | Program/SD's/DD's/CD's/Entitlements/Building Permit | 1040 | HRS | 115 | 119600 | DDB
5 | Specifications | 1 | LS | 6500 | 6500 | ProSpec
6 | Civil Engineering | 1 | LS | 85000 | 85000 | EES - Building
7 | Civil Engineering | 1 | LS | 15460 | 15460 | EES - Denver Water Main Replacement
8 | Structural Engineering | 1 | LS | 100000 | 100000 | Monroe Newell/ERA Ericksen Roed Associates
9 | Fire Protection Engineering |  | LS | 0 | 0 | Included - Central Fire Protection
10 | Plumbing Engineering |  | LS | 0 | 0 | Included - JCAA/Canyon Plumbing
11 | HVAC Engineering |  | LS | 0 | 0 | Included - JCAA/Marxaire
12 | Electrical Engineering |  | LS | 0 | 0 | Included - Rossie Engineering/Hi-Tech
13 | Sound Engineering | 1 | LS | 9000 | 9000 | EDI - No testing
14 | Interior design | 200 | HRS | 85 | 17000 | DDB
15 | Landscape Architecture | 1 | EA | 7500 | 7500 | TCK Landscape Architecture
16 | Survey - Building | 1 | EA | 15000 | 15000 | Powers Surveying - Design phase
17 | Survey - Denver Water Water Main Replacement | 1 | EA | 29960 | 29960 | Survwest - Grade A survey (ROW)
18 | Survey - Denver Water Water Main Replacement | 1 | EA | 8300 | 8300 | Survwest - Construction surveying
19 | Geotechnical report (soils) | 1 | EA | 7500 | 7500 | RMG
01 - General Requirements |  |  |  |  | 2206357
02 - Site Construction
# | DESCRIPTION | QTY | UNIT | UNIT PRICE | COST | COMMENTS | COST CODE | TYPE
1 | Trash removal - roll off dumpsters | 30 | EA | 385 | 11550 | DDB
2 | Vehicle tracking control | 1 | EA | 15000 | 15000 | Frontage stabilization system for - Pre-cast sent and pump trucks
3 | BMP, erosion and sediment control | 1 | LS | 15000 | 15000
4 | Building & site demolition |  | LS |  | 0 | Excluded
5 | Tree removal |  | LS | 0 | 0 | Excluded - No trees on site
6 | Xcel - gas and electric meter removal |  | LS | 0 | 0 | By owner - Shown in summary
7 | Water shut off and final bill |  | LS | 0 | 0 | By owner - Shown in summary
8 | Hazardous material abatement |  | EA | 0 | 0 | Excluded - Commercial building, should be NONE
9 | Clear & grub site |  | LF | 0 | 0 | Included in Andraos Construction
10 | Excavation/over-excavation/backfill
11 | Over-excavation - Export | 10370.3704 | YD | 18.25 | 189259.2593 | Lighting Ventures
12 | Excavation - Structural | 500 | YD | 18.25 | 9125 | Lighting Ventures
13 | Back-fill - Import/backfill | 1000 | YD | 23 | 23000 | Crushed self compacting recycled concrete - back fill at foundation walls
14 | Rough grading |  | YD | 0 | 0 | Included in excavation cost
15 | Fine grading | 18191 | SF | 1.15 | 20919.65
16 | Shoring | 8400 | FSF | 32 | 268800 | Schnabel - Based on 14 feet
17 | Right of way permits | 1 | LS | 35000 | 35000 | Allowance
18 | Fire hydrant |  | LS | 0 | 0 | Excluded
19 | Building services
20 | 2 Inch Domestic water service | 1 | LS | 24500 | 24500
21 | 6 Inch fire main | 1 | LS | 33000 | 33000
22 | 6 inch sewer line | 1 | LS | 12500 | 12500
23 | Underground roof storm, storm and water quality
24 | Material - ONLY |  |  |  | 0 | Excluded
25 | Installation |  |  |  | 0 | Excluded
26 | Backfill - Water quality - Class 6 | 1000 | YDS | 23 | 23000 | Backfill for the garage slab
27 | Traffic control | 1 | LS | 15000 | 15000 | Allowance
28 | Sawcut & asphalt/concrete removal @ ROW |  | LS | 0 | 0 | Andraos Construction - Included in concrete cost
29 | Storm sewer - inlet and outlet structures. 2 inlets |  | LS | 0 | 0 | Excluded
30 | Sand & oil interceptor - 800 gallon |  | LS | 0 | 0 | Canyon Plumbing - Included in plumbing cost
31 | Grease interceptor - 2500 gallon |  | LS | 0 | 0 | Canyon Plumbing - Included in plumbing cost
32 | Denver water main | 1 | LS | 365000 | 365000 | 8-inch main replacement 7th-8th
33 | Landscaping
34 | Front | 1 | LS | 7500 | 7500 | On grade ONLY - ROW - Trees ONLY - With drip irrigation
35 | Trash enclosure |  | LS | 0 | 0 | Excluded
36 | Permanent site signage |  | LS | 0 | 0 | Denver Print Company - Included in sign cost
37 | Monument signage |  | LS | 0 | 0 | Denver Print Company - Included in sign cost
38 | Bike racks - Materials - Front | 10 | EA | 238.66 | 2386.6005 | Page Specialties
39 | Bike racks - Labor | 4 | HRS | 41.5 | 166 | Quality Trim Installation
40 | Site amenities |  | LS | 0 | 0 | Excluded
02 - Site Construction |  |  |  |  | 1070706.5098
03 - Concrete
# | DESCRIPTION | QTY | UNIT | UNIT PRICE | COST | COMMENTS | COST CODE | TYPE
1 | Foundation |  |  |  | 0
2 | Wall | 8400 | FSF | 28 | 235200 | Shot crete wall 12' inches thick
3 | Mat footings | 225 | YDS | 550 | 123750 | Stair towers and Elevator towers (Mat foundations 20 feet x 50 feet by 3 feet thick)
4 | Strip footing | 240 | YDS | 550 | 132000 | 400 feet x 8 feet widw x 2 feet deep
5 | Pad footing | 170 | YDS | 550 | 93500 | 10 15 feet x 15 feet x 2 feet deep
6 | Tower crane pad 1 | 1 | LS | 55000 | 55000 | Lithko Contracting
7 | Structural system - Precast (Wall, columns, floors, elevator towers, stair towers and stairs) | 91780 | SF | 29.51 | 2708427.8 | WC - Pre Cast - Structure
8 | Structural system - Precast (Thin wall system) | 28000 | SF | 85 | 2380000 | WC - Pre Cast - Architectural pre-cast included, thin wall system, drywall ready
9 | Concrete pumping - structural concrete and flatwork | 15 | Pours | 2500 | 37500 | DDB
10 | Washouts - Structural concrete & flatwork | 15 | EA | 450 | 6750 | DDB
11 | Concrete retaining walls |  |  |  | 0 | Excluded
12 | Slab on grade - 5" garage | 18191 | SF | 5.85 | 106417.35 | Andraos Construction - Based on 90/40 structural fiber mesh
13 | ROW sidewalk | 100 | LF | 85 | 8500 | Andraos Construction - All required prep included
14 | ROW curb & gutter | 100 | LF | 85 | 8500 | Andraos Construction - All required prep included
15 | ROW - remove & replace back alley | 1800 | SF | 14 | 25200 | Andraos Construction - Assume 8" thick
16 | Slabs - Elevator pits | 216 | SF | 12 | 2592 | Andraos Construction
17 | Concrete wheel stops | 31 | EA | 225 | 6975 | Apex Paving
18 | Concrete flatwork - 4 inch structural concrete diaphragm | 91780 | SF | 5.45 | 500201 | Andraos Construction/Lithko - Based on 90/40 structural fiber mesh
19 | Trickle channel/drain pan |  | SF | 0 | 0 | Excluded
20 | Light pole bases |  | SF | 0 | 0 | Excluded
21 | Bollards | 10 | EA | 650 | 6500 | Andraos Construction - 6 inch steel filled with concrete
22 | Trench drain |  | EA | 0 | 0 | Excluded
23 | Gyp-crete 1 1/2 |  | EA | 0 | 0 | Excluded
24 | Asphalt patching at ROW |  | EA | 0 | 0 | Included in utility package cost
25 | Stripping | 31 | LS | 150 | 4650 | Apex Paving
26 | Concrete sealing |  | LS | 0 | 0 | Goodman Tile and Stone - Included in finishes
27 | Concrete coatings/overlays |  | LS | 0 | 0 | Excluded
03 - Concrete |  |  |  |  | 6441663.15
04 - Masonry
# | DESCRIPTION | QTY | UNIT | UNIT PRICE | COST | COMMENTS | COST CODE | TYPE
1 | Brick |  | SF | 0 | 0 | Excluded
2 | CMU |  | SF | 0 | 0 | Excluded
3 | Elevator shaft in-fill |  | EA | 0 | 0 | Excluded
4 | Trask chute in-fill |  | EA | 0 | 0 | Excluded
5 | Hollow metal door grouting at fire walls |  | EA | 0 | 0 | Excluded
04 - Masonry |  |  |  |  | 0
05 - Metals
# | DESCRIPTION | QTY | UNIT | UNIT PRICE | COST | COMMENTS | COST CODE | TYPE
1 | Structural beams & columns for wood frame - included in framing |  | LS | 0 | 0 | Excluded
2 | Embed plates - podium to wood & podium to under deck, cmu |  | LS | 0 | 0 | Excluded
3 | Metal decking |  | LS | 0 | 0 | Excluded
4 | Steel support for beams and permeate hoist |  | LS | 0 | 0 | Excluded
5 | Form angle |  | LF | 0 | 0 | Excluded
6 | Misc. angles, connections, steel parts - form angle | 150 | LF | 55 | 8250 | Safety rail cable (temporary)
7 | Angle to support brick |  | LF | 0 | 0 | Excluded
8 | Metal ladders - Elevator ONLY |  | LF | 0 | 0 | ThyssenKrupp - Included in elevator cost
9 | Metal elevator grates @ bottom of pit | 2 | EA | 550 | 1100 | Victor Metal Works
10 | Trench drain covers - Tree grates - ROW landscaping | 3 | EA | 3500 | 10500 | Victor Metal Works
11 | Steel canopy at entrance. Frame and cover | 40 | LF | 185 | 7400 | Victor Metal Works - 4 feet wide x 20 feet long
12 | Exterior guardrails at roof | 75 | LF | 115 | 8625 | Victor Metal Works - Included in decorative steel costs - ONLY as outlined herein - No front railing systems along Santa Fe
13 | Decorative steel trellis | 1 | LS | 15000 | 15000 | Victor Metal Works - At roof deck- Allowance
14 | Balcony railing - Units ONLY
15 | Unit A - D 2 | 56 | EA | 4500 | 252000 | Victor Metal Works - Drip thru with railing 5 FT x 10 FT
16 | Steel stairs guardrails and handrails
17 | Stair tower 1 | 6 | Stories | 4000 | 24000 | Victor Metal Works - Roof access stair ONLY
18 | Stair tower 2 | 5 | Stories | 4000 | 20000 | Victor Metal Works
19 | Misc. site welding | 40 | HRS | 150 | 6000 | Victor Metal Works
05 - Metals |  |  |  |  | 352875
06 - Wood & Plastics
# | DESCRIPTION | QTY | UNIT | UNIT PRICE | COST | COMMENTS | COST CODE | TYPE
1 | Rough framing - labor and material |  | EA | 0 | 0 | Excluded
2 | Rough framing - trusses |  | EA | 0 | 0 | Excluded
3 | Interior soffits & backout |  | EA | 0 | 0 | Excluded
4 | Pre-fab stairs |  | EA | 0 | 0 | Excluded
5 | Glulam treads |  | EA | 0 | 0 | Excluded
6 | Temp wood treads and stairs |  | EA | 0 | 0 | Excluded
7 | Misc. blocking
8 | Units A - D 2 - Inside units for mounting | 56 | EA | 650 | 36400 | Quality Trim Installation - Units ONLY
9 | Parapets | 560 | LF | 5 | 2800 | Quality Trim Installation - Nailers at parapets and wall caps
10 | Shim & shave wood framing |  | EA | 0 | 0 | Excluded
11 | Misc. carpentry labor | 640 | HRS | 45 | 28800 | DDB
12 | Interior trim - labor & materials - base, common areas | 985 | LF | 5.45 | 5368.25 | Quality Trim Installation
13 | Interior trim - labor & materials - base, case, and closets (shelve and rod)
14 | Unit A - D 2 | 56 | EA | 975 | 54600 | Quality Trim Installation
06 - Wood & Plastics |  |  |  |  | 127968.25
07 - Thermal & Moisture Protection
# | DESCRIPTION | QTY | UNIT | UNIT PRICE | COST | COMMENTS | COST CODE | TYPE
1 | Waterproofing - Underground parking | 8400 | SF | 8 | 67200 | WC - Five Star underground parking - Tremco 250GC system
2 | Waterproofing - Court yard |  | SF | 0 | 0 | Excluded
3 | Waterproofing - Exterior skin at brick |  | SF | 0 | 0 | Excluded
4 | Joint sealants & caulking - Pre cast |  | LS | 0 | 0 | Included in Wells Concrete
5 | Joint sealants & caulking - Building |  | LF | 0 | 0 | Included in Wells Concrete
6 | Batt Insulation - Total insulation | 91780 | SF | 2.05 | 188149 | Spec 7 - R-30 on roof included in - Academy Roofing
7 | Fire caulking | 91780 | SF | 0.25 | 22945 | DDB
8 | Draft/fire stopping |  |  |  | 0 | Spec 7 - Included in insulation cost
9 | TPO roofing | 18823 | SF | 17.85 | 335990.55 | Academy Roofing - 40 mill fully adhered vapor barrier - 725 TR, fully tapered, 1/2 dens deck, TPO cool roof SRI - 72, R-30 ridge insulation on the roof
10 | Roof pavers
11 | Roof Deck - Reduced | 3500 | SF | 32.5 | 113750 | Academy Roofing
12 | Misc. metal flashings, parapet cap | 575 | LF | 20 | 11500 | Academy Roofing
13 | Gutters and downspouts - At upper roofs ONLY | 1 | LS | 2500 | 2500 | Academy Roofing
14 | Skylights |  | LS | 0 | 0 | Excluded
15 | Walk pads - As required by the manufacture ONLY |  | LS | 0 | 0 | Excluded
16 | Condenser pads/isolation pads |  | LS | 0 | 0 | Excluded
17 | Stucco system |  | LS | 0 |  | Excluded
07 - Thermal & Moisture Protection |  |  |  |  | 742034.55
08 - Doors & Windows
# | DESCRIPTION | QTY | UNIT | UNIT PRICE | COST | COMMENTS | COST CODE | TYPE
1 | Window package Material ONLY - Units ONLY |  |  |  |  | Included in Wells Concrete
2 | Window install |  |  |  |  | Included in Wells Concrete
3 | Storefront systems
4 | Retail entry and lobby entry doors | 10 | EA | 2200 | 22000 | M&W Glass - 2 Retail and 2 Lobby (Single doors)
5 | Store glass retail | 750 | SF | 50 | 37500 | M&W Glass
6 | Steel support - Storefront |  | SF | 0 | 0 | Excluded
7 | Balcony doors |  | EA | 0 | 0 | Included in Wells Concrete
8 | Garage door underground parking | 1 | EA | 16950.52 | 16950.52 | American Garage Door
9 | Elevator smoke curtains | 10 | EA | 6500 | 65000 | Smoke curtain
10 | Hollow metal door, frame, hardware, install
11 | Stair towers | 12 | EA | 1650 | 19800 | Quality Trim Installation
12 | Mechanical rooms | 10 | EA | 1650 | 16500 | Quality Trim Installation
13 | Ground level | 2 | EA | 1650 | 3300 | Quality Trim Installation
14 | Pre-hung hollow core door (Labor and Material) - Units ONLY
15 | Unit A - D 2 | 56 | EA | 1280 | 71680 | Quality Trim Installation
16 | Door hardware Labor & material - Unit entry | 56 | EA | 150 | 8400 | Quality Trim Installation
17 | Door hardware Labor & material - Unit interior doors Hollow core | 280 | EA | 65 | 18200 | Quality Trim Installation
18 | Door hardware Labor & material - Unit interior doors hardware | 280 | EA | 45 | 12600 | Quality Trim Installation
19 | Misc. carpentry labor | 640 | HRS | 55 | 35200 | DDB
08 - Doors & Windows |  |  |  |  | 327130.52
09 - Finishes
# | DESCRIPTION | QTY | UNIT | UNIT PRICE | COST | COMMENTS | COST CODE | TYPE
1 | Metal stud framing - Walls Units and Common Areas (Trash, Corridors and Fitness)
2 | Interior | 73589 | SF | 4.1765 | 307342.2941 | SNR Contractors - 20 GA viper studs for the interior walls, 3 5/8 inch, corridors 6 inch at 24 inches OC
3 | Retail
4 | Drywall - White box |  |  |  |  | GREY BOX - No finishes
5 | Drywall - Walls Units and Common Areas (Trash, Corridors and Fitness)
6 | Interior | 73589 | SF | 4.1176 | 303013.5294 | SNR Contractors - Two layers of 5/8 inch drywall on unit common wall and corridors surfaces
7 | Drywall - Ceiling System Units
8 | Grid X ceiling | 73589 | SF | 3.3529 | 246739.5882 | SNR Contractors - Grid X ceiling
9 | Isolation clip | 73589 | SF | 2.9176 | 214706.7294 | SNR Contractors - Isolation clips
10 | Drywall on grid X ceiling | 73589 | SF | 1.7647 | 129862.9412 | SNR Contractors - One layer of 5/8 drywall
11 | Drywall patching & paint touch ups | 73589 | SF | 0.3 | 22076.7 | SNR Contractors
12 | Acoustical tile ceiling w/ grid | 2801 | SF | 6.1765 | 17300.2941 | SNR Contractors
13 | Interior painting | 73589 | SF | 3.35 | 246523.15 | SNR Contractors
14 | Exterior painting
15 | Exterior doors | 24 | EA | 750 | 18000 | SNR Contractors
16 | Bollards | 10 | EA | 250 | 2500 | SNR Contractors
17 | Steel lintels |  | LS |  | 0 | Excluded
18 | Staining |  | EA | 0 | 0 | Excluded
19 | Sealed concrete floor at mechanical rooms and stair towers | 1 | LS | 45000 | 45000 | Goodman Tile & Stone
20 | Unit floors - Pre Eng. Wood
21 | Unit A - 12
22 | Priming of the concrete floor | 6494.4 | SF | 1.32 | 8572.608 | Goodman Tile & Stone
23 | Sound mat | 6494.4 | SF | 1.77 | 11495.088 | Goodman Tile & Stone
24 | Material | 6494.4 | SF | 2.55 | 16560.72 | Goodman Tile & Stone
25 | Labor | 6494.4 | SF | 2.75 | 17859.6 | Goodman Tile & Stone
26 | Unit B - 12
27 | Priming of the concrete floor | 8091.6 | SF | 1.32 | 10680.912 | Goodman Tile & Stone
28 | Sound mat | 8091.6 | SF | 1.77 | 14322.132 | Goodman Tile & Stone
29 | Material | 8091.6 | SF | 2.55 | 20633.58 | Goodman Tile & Stone
30 | Labor | 8091.6 | SF | 2.75 | 22251.9 | Goodman Tile & Stone
31 | Unit C - 4
32 | Priming of the concrete floor | 3216.4 | SF | 1.32 | 4245.648 | Goodman Tile & Stone
33 | Sound mat | 3216.4 | SF | 1.77 | 5693.028 | Goodman Tile & Stone
34 | Material | 3216.4 | SF | 2.55 | 8201.82 | Goodman Tile & Stone
35 | Labor | 3216.4 | SF | 2.75 | 8845.1 | Goodman Tile & Stone
36 | Unit C 1 - 8
37 | Priming of the concrete floor | 6010.4 | SF | 1.32 | 7933.728 | Goodman Tile & Stone
38 | Sound mat | 6010.4 | SF | 1.77 | 10638.408 | Goodman Tile & Stone
39 | Material | 6010.4 | SF | 2.55 | 15326.52 | Goodman Tile & Stone
40 | Labor | 6010.4 | SF | 2.75 | 16528.6 | Goodman Tile & Stone
41 | Unit C 2 - 4
42 | Priming of the concrete floor | 2926 | SF | 1.32 | 3862.32 | Goodman Tile & Stone
43 | Sound mat | 2926 | SF | 1.77 | 5179.02 | Goodman Tile & Stone
44 | Material | 2926 | SF | 2.55 | 7461.3 | Goodman Tile & Stone
45 | Labor | 2926 | SF | 2.75 | 8046.5 | Goodman Tile & Stone
46 | Unit D 1 - 8
47 | Priming of the concrete floor | 9160.8 | SF | 1.32 | 12092.256 | Goodman Tile & Stone
48 | Sound mat | 9160.8 | SF | 1.77 | 16214.616 | Goodman Tile & Stone
49 | Material | 9160.8 | SF | 2.55 | 23360.04 | Goodman Tile & Stone
50 | Labor | 9160.8 | SF | 2.75 | 25192.2 | Goodman Tile & Stone
51 | Unit D 2 - 8
52 | Priming of the concrete floor | 9160.8 | SF | 1.32 | 12092.256 | Goodman Tile & Stone
53 | Sound mat | 9160.8 | SF | 1.77 | 16214.616 | Goodman Tile & Stone
54 | Material | 9160.8 | SF | 2.55 | 23360.04 | Goodman Tile & Stone
55 | Labor | 9160.8 | SF | 2.75 | 25192.2 | Goodman Tile & Stone
56 | Corridors - commercial carpet tiles (unit levels)
57 | Material | 854 | YDS | 25 | 21350 | Goodman Tile & Stone
58 | Labor | 854 | YDS | 12.5 | 10675 | Goodman Tile & Stone
59 | Elevator - commercial carpet tiles | 2 | EA | 450 | 900 | Goodman Tile & Stone
60 | Main level - commercial carpet tiles
61 | Corridor and Egress
62 | Material | 170 | YDS | 25 | 4250 | Goodman Tile & Stone
63 | Labor | 170 | YDS | 12.5 | 2125 | Goodman Tile & Stone
64 | Fitness |  |  |  | 0
65 | Material | 1211 | SF | 9.5 | 11504.5 | Goodman Tile & Stone
66 | Labor | 1211 | SF | 6.5 | 7871.5 | Goodman Tile & Stone
67 | Bath floor tile - Units ONLY (Material 12 x 24) $4.35
68 | Unit A - 12
69 | Priming of the concrete floor | 448.8 | SF | 1.32 | 592.416 | Goodman Tile & Stone
70 | Sound mat | 448.8 | SF | 5.51 | 2472.888 | Goodman Tile & Stone
71 | Material (Setting) | 448.8 | SF | 5.9 | 2647.92 | Goodman Tile & Stone
72 | Labor | 448.8 | SF | 6.5 | 2917.2 | Goodman Tile & Stone
73 | Base (Tile) - Labor | 192 | LF | 5 | 960 | Goodman Tile & Stone
74 | Unit B - 12
75 | Priming of the concrete floor | 448.8 | SF | 1.32 | 592.416 | Goodman Tile & Stone
76 | Sound mat | 448.8 | SF | 5.51 | 2472.888 | Goodman Tile & Stone
77 | Material (Setting) | 448.8 | SF | 5.9 | 2647.92 | Goodman Tile & Stone
78 | Labor | 448.8 | SF | 6.5 | 2917.2 | Goodman Tile & Stone
79 | Base (Tile) - Labor | 192 | LF | 5 | 960 | Goodman Tile & Stone
80 | Unit C - 4
81 | Priming of the concrete floor | 176 | SF | 1.32 | 232.32 | Goodman Tile & Stone
82 | Sound mat | 176 | SF | 5.51 | 969.76 | Goodman Tile & Stone
83 | Material (Setting) | 176 | SF | 5.9 | 1038.4 | Goodman Tile & Stone
84 | Labor | 176 | SF | 6.5 | 1144 | Goodman Tile & Stone
85 | Base (Tile) - Labor | 72 | LF | 5 | 360 | Goodman Tile & Stone
86 | Unit C 1- 8
87 | Priming of the concrete floor | 352 | SF | 1.32 | 464.64 | Goodman Tile & Stone
88 | Sound mat | 352 | SF | 5.51 | 1939.52 | Goodman Tile & Stone
89 | Material (Setting) | 352 | SF | 5.9 | 2076.8 | Goodman Tile & Stone
90 | Labor | 352 | SF | 6.5 | 2288 | Goodman Tile & Stone
91 | Base (Tile) - Labor | 144 | LF | 5 | 720 | Goodman Tile & Stone
92 | Unit C 2 - 4
93 | Priming of the concrete floor | 176 | SF | 1.32 | 232.32 | Goodman Tile & Stone
94 | Sound mat | 176 | SF | 5.51 | 969.76 | Goodman Tile & Stone
95 | Material (Setting) | 176 | SF | 5.9 | 1038.4 | Goodman Tile & Stone
96 | Labor | 176 | SF | 6.5 | 1144 | Goodman Tile & Stone
97 | Base (Tile) - Labor | 72 | LF | 5 | 360 | Goodman Tile & Stone
98 | Unit D 1 - 8
99 | Priming of the concrete floor | 453.2 | SF | 1.32 | 598.224 | Goodman Tile & Stone
100 | Sound mat | 453.2 | SF | 5.51 | 2497.132 | Goodman Tile & Stone
101 | Material (Setting) | 453.2 | SF | 5.9 | 2673.88 | Goodman Tile & Stone
102 | Labor | 453.2 | SF | 6.5 | 2945.8 | Goodman Tile & Stone
103 | Base (Tile) - Labor | 152 | LF | 5 | 760 | Goodman Tile & Stone
104 | Unit D 2 - 8
105 | Priming of the concrete floor | 453.2 | SF | 1.32 | 598.224 | Goodman Tile & Stone
106 | Sound mat | 453.2 | SF | 5.51 | 2497.132 | Goodman Tile & Stone
107 | Material (Setting) | 453.2 | SF | 5.9 | 2673.88 | Goodman Tile & Stone
108 | Labor | 453.2 | SF | 6.5 | 2945.8 | Goodman Tile & Stone
109 | Base (Tile) - Labor | 152 | LF | 5 | 760 | Goodman Tile & Stone
110 | Shower pan - Units ONLY |  |  | 0
111 | Material (Setting) | 16 | EA | 450 | 7200 | Goodman Tile & Stone
112 | Labor | 16 | EA | 380 | 6080 | Goodman Tile & Stone
113 | Shower floor tile - Units ONLY (Material) $9.10 |  |  | 0
114 | Material (Setting) | 16 | EA | 185 | 2960 | Goodman Tile & Stone
115 | Labor | 16 | EA | 225 | 3600 | Goodman Tile & Stone
116 | Shower floor wall - Units ONLY (Material) $2.50 |  |  | 0
117 | Material (Setting) | 1865.6 | SF | 3.8 | 7089.28 | Goodman Tile & Stone
118 | Labor | 1865.6 | EA | 5.75 | 10727.2 | Goodman Tile & Stone
119 | Bath tub wall - Units ONLY (Material) $2.50 |  |  | 0
120 | Material (Setting) | 5359.2 | EA | 3.8 | 20364.96 | Goodman Tile & Stone
121 | Labor | 5359.2 | EA | 5.75 | 30815.4 | Goodman Tile & Stone
122 | Kitchen backsplashes - Units ONLY (Material) $5.60
123 | Units A - D2 - Labor | 1396 | SF | 12 | 16752 | Goodman Tile & Stone
124 | Units A - D2 - Material (Tile and Setting) | 1396 | SF | 5.6 | 7817.6 | Goodman Tile & Stone
125 | Countertops - Kitchens and islands
126 | Units A - D2 - Labor | 2776 | SF | 28 | 77728 | Goodman Tile & Stone
127 | Units A - D2 - Material | 2776 | SF | 27.06 | 75118.56 | Goodman Tile & Stone
128 | Countertops -Bathroom vanities (Master and Guess)
129 | Units A - D2 - Labor | 704 | SF | 28 | 19712 | Goodman Tile & Stone
130 | Units A - D2 - Material | 704 | SF | 27.06 | 19050.24 | Goodman Tile & Stone
131 | Cabinets & hardware MATERIAL ONY - Units ONLY
132 | Unit A1 | 56 | EA | 3550 | 198800 | Concept 32
133 | Cabinets & hardware LABOR ONY - Units ONLY
134 | Unit A1 | 56 | EA | 1250 | 70000 | Quality Trim Installation
135 | FRP walls & trim |  |  |  | 0 | Excluded
09 - Finishes |  |  |  |  | 2616722.0625
10 - Specialties
# | DESCRIPTION | QTY | UNIT | UNIT PRICE | COST | COMMENTS | COST CODE | TYPE
1 | Shower doors - Units ONLY | 16 | EA | 1150 | 18400 | D Units ONLY
2 | Mirrors - Units ONLY
3 | Unit A - D 2 | 56 | EA | 175 | 9800 | M&W Glass
4 | Bathroom accessories - Units ONLY (Material)
5 | Unit A - D 2 | 1 | LS | 7944.11 | 7944.11 | Quality Trim Installation - Schedule in Owner's program
6 | Bathroom accessories - Units ONLY (Labor)
7 | Unit A - D 2 | 56 | EA | 62.25 | 3486 | Quality Trim Installation
8 | Fire extinguishers/cabinets | 15 | EA | 350 | 5250 | Quality Trim Installation - Every 75 feet of travel distance
9 | Interior signage, unit numbers | 91780 | LS | 0.25 | 22945 | Denver Print Company - Allowance
10 | Mailboxes - Material | 1 | LS | 7500 | 7500 | Page Specialties
11 | Mailboxes - Labor | 16 | HRS | 41.5 | 664 | Quality Trim Installation
12 | Knox box - Labor and material | 1 | LS | 350 | 350 | Quality Trim Installation
13 | Grab bars - ADA units - Labor and material | 2 | EA | 450 | 900 | Quality Trim Installation
14 | Access panels
15 | Corridors - Fire suppression system | 5 | EA | 405 | 2025 | SNR Contractors - Fire protection in the corridors - 1 per level
10 - Specialties |  |  |  |  | 79264.11
11 - Equipment
# | DESCRIPTION | QTY | UNIT | UNIT PRICE | COST | COMMENTS | COST CODE | TYPE
1 | Appliance w/ install |  |  |  | 0
2 | Unit A - D 2 | 56 | EA | 2850 | 159600 | Specialty Appliances (Frig, Micro, Range (Electric), Dishwasher, Washer/Dryer)
3 | Specialty equipment |  | ES | 0 | 0 | Excluded
11 - Equipment |  |  |  |  | 159600
12 - Furnishings
# | DESCRIPTION | QTY | UNIT | UNIT PRICE | COST | COMMENTS | COST CODE | TYPE
1 | FFE |  |  |  | 0 | Excluded
2 | Window treatment |  |  |  | 0 | Excluded
12 - Furnishings |  |  |  |  | 0
13 - Specialty Construction
# | DESCRIPTION | QTY | UNIT | UNIT PRICE | COST | COMMENTS | COST CODE | TYPE
1 | Fire sprinklers
2 | Underground Parking | 18191 | SF | 1.75 | 31834.25 | Central Fire Protection - Wet system - Exposed concrete ceilings
3 | First level common area | 9406 | SF | 2.25 | 21163.5 | Central Fire Protection - Wet system - Exposed concrete ceilings
4 | Retail | 8785 | SF | 1.75 | 15373.75 | Central Fire Protection - Wet system - Exposed concrete ceilings
5 | Condos Levels | 64804 | SF | 3.75 | 243015 | Central Fire Protection - Wet system - Finish ceiling with concealed heads
6 | Fire alarm | 91780 | SF | 1.72 | 157861.6 | Hi-Tech Electric
7 | Access control | 1 | LS | 7500 | 7500 | Hi-Tech Electric - Allowance
8 | Solar panels |  | LS | 0 | 0 | Excluded
9 | Fire pump and transfer switch |  | LS | 0 | 0 | Excluded
10 | Radio amplification system, cell booster |  | LS | 0 | 0 | Excluded
11 | Specialty rooms - Generator |  | LS | 0 | 0 | Hi-Tech Electric - Included In electrical cost
12 | Security - Cameras | 1 | LS | 7500 | 7500 | Hi-Tech Electric - Allowance
13 - Specialty Construction |  |  |  |  | 484248.1
14 - Conveying Systems
# | DESCRIPTION | QTY | UNIT | UNIT PRICE | COST | COMMENTS | COST CODE | TYPE
1 | Elevators | 2 | EA | 153025 | 306050 | ThyessKrupp's - 2 Cars
2 | Trash chute | 2 | EA | 15000 | 30000 | Colorado Trash Chute
3 | Trash compactor |  |  |  | 0 | Excluded
14 - Conveying Systems |  |  |  |  | 336050
15 - Mechanical
# | DESCRIPTION | QTY | UNIT | UNIT PRICE | COST | COMMENTS | COST CODE | TYPE
1 | Underslab piping, including s&o |  | EA | 0 | 0 | Canyon Plumbing - No gas piping (ONLY at Penthouses)
2 | Replace water lines in existing buildings - Denver Water Main Replacement | 27 | EA | 550 | 14850 | Canyon Plumbing - Denver Water Main Replacement
3 | Roof top - ONLY | 250 | LF | 23.5 | 5875 | Canyon Plumbing
4 | Rough plumbing/finish trim
5 | Garage |  | SF | 0 | 0 | Canyon Plumbing
6 | Underground drain | 18191 | SF | 0.35 | 6366.85 | Canyon Plumbing
7 | Pumps (Foundation drain and Sand/Oil) | 1 | EA | 5500 | 5500 | Canyon Plumbing
8 | Retail
9 | Water stub | 2 | EA | 1500 | 3000 | Canyon Plumbing - 3/4 water line stub
10 | Condos - Units | 45638 | SF | 11 | 502018 | Canyon Plumbing - No gas piping (ONLY at Penthouses)
11 | Sand & oil interceptor - 85 gallon | 1 | EA | 5000 | 5000 | Canyon Plumbing
12 | Grease interceptor - 2500 gallon |  |  |  | 0 | Excluded
13 | Roof drainage system with over flows | 6 | EA | 7500 | 45000 | Canyon Plumbing
14 | Elevator sump and pump | 2 | EA | 3200 | 6400 | Canyon Plumbing
15 | Water heater install | 56 | EA | 1687 | 94472 | Canyon Plumbing
16 | Backflow preventer and watermain | 2 | EA | 3000 | 6000 | Canyon Plumbing - based on 2 inch domestic water
17 | Gore drilling (Plumbing ONLY) | 56 | EA | 295 | 16520 | Canyon Plumbing
18 | Hose bibs, floor drains, ice makers |  | EA | 0 | 0 | Canyon Plumbing - Included in plumbing cost
19 | Hot water heaters |  | EA | 0 | 0 | Canyon Plumbing - Included in plumbing cost
20 | Roof drains from roof to exterior |  | EA | 0 | 0 | Canyon Plumbing - Included in plumbing cost
21 | Pipe insulation |  | EA | 0 | 0 | Canyon Plumbing - Included in plumbing cost
22 | Recirc pump |  | EA | 0 | 0 | Canyon Plumbing - Included in plumbing cost
23 | Sewage ejectors |  | EA | 0 | 0 | Canyon Plumbing - Included in plumbing cost
24 | Backflow preventers |  | EA | 0 | 0 | Canyon Plumbing - Included in plumbing cost
25 | Irrigation stub |  | EA | 0 | 0 | Canyon Plumbing - Included in plumbing cost
26 | Drinking fountains |  | EA | 0 | 0 | Excluded
27 | Plumbing fixtures - Units ONLY
28 | Unit A - D2 | 1 | LS | 106149.6 | 106149.6 | Canyon Plumbing - Schedule attached to Owner's program
29 | Oil smart pump for elevator |  |  |  | 0 | Canyon Plumbing - Included in plumbing cost
30 | Mechanical system
31 | Garage - Underground | 18191 | SF | 3.47 | 63122.77 | Marxaire
32 | Generator | 10 | LF | 850 | 8500 | Marxaire - 8 inch round exhaust 10'-0" lineal feet
33 | Condos - Units | 45638 | SF | 18.4 | 839739.2 | Marxaire - V-Tac, mechanical system
34 | Common | 1 | LS | 50000 | 50000 | Corridor - Mini splits
35 | Exhaust fans - Buster fans for dryers |  | EA | 0 | 0 | Marxaire - Included in HVAC costs
36 | Exhaust fans trim - Exterior |  | EA | 0 | 0 | Marxaire - Included in HVAC costs
37 | Mounting units to the ceiling |  | EA | 0 | 0 | Excluded
38 | Condensate line |  | EA | 0 | 0 | Canyon Plumbing - Included in plumbing cost
39 | Exhaust system CO 2 |  | EA | 0 | 0 | Marxaire - Included in HVAC costs
40 | Duct cleaning |  | EA | 0 | 0 | Excluded
41 | Air balancing |  | EA | 0 | 0 | Marxaire - Included in HVAC costs
42 | Fire/smoke dampers |  | EA | 0 | 0 | Marxaire - Included in HVAC costs
43 | Hydronic system/boiler |  | EA | 0 | 0 | Excluded
44 | Radiant floor heat |  | EA | 0 | 0 | Excluded
45 | Sub meters
46 | Units | 56 | EA | 450 | 25200 | Minol - Water and Electric
47 | Retail 4 units | 4 | EA | 450 | 1800 | Minol - Water and Electric
48 | Common gas | 1 | EA | 350 | 350 | Minol - Water - Common area roof top ONLY
49 | Common water | 1 | EA | 350 | 350 | Minol - Water - Common area irrigation
50 | Common electrical | 1 | EA | 350 | 350 | Minol - Electric - Common area house panel
15 - Mechanical |  |  |  |  | 1806563.42
16 - Electrical
# | DESCRIPTION | QTY | UNIT | UNIT PRICE | COST | COMMENTS | COST CODE | TYPE
1 | Electrical system - rough & trim
2 | Underground Parking | 18191 | SF | 3.65 | 66397.15 | Hi-Tech Electric
3 | Service | 1 | LS | 325000 | 325000 | Hi-Tech Electric
4 | Retail | 8785 | SF | 1.25 | 10981.25 | Hi-Tech Electric
5 | Condos - Units | 45638 | SF | 19.25 | 878531.5 | Hi-Tech Electric
6 | Low Voltage - Units | 45638 | SF | 1.2 | 54765.6 | Hi-Tech Electric
7 | Underground piping low-volt |  | EA | 0 | 0 | Hi-Tech Electric - Included In electrical cost
8 | Temp electrical service - panel & turtles |  | EA | 0 | 0 | Hi-Tech Electric - Included In electrical cost
9 | Low voltage lighting |  | EA | 0 | 0 | Hi-Tech Electric - Included In electrical cost
10 | Low voltage audio/video |  | EA | 0 | 0 | Excluded
11 | Security wiring |  | EA | 0 | 0 | Hi-Tech Electric - Included In electrical cost, as required for the camera scope ONLY
12 | Electrical fixtures - Units ONLY
13 | Unit A - D 2 | 1 | LS | 63023.28 | 63023.28 | Hi-Tech Electric - Schedule attached to the Owner's program
14 | Permanent generator |  | EA | 0 | 0 | Hi-Tech Electric - Included In electrical cost
15 | Electrical raceways |  | EA | 0 | 0 | Hi-Tech Electric - Included In electrical cost
16 | Electrical heating |  | EA | 0 | 0 | Marxaire - Included in HVAC costs
17 | Sub-metering's |  | EA | 0 | 0 | Minol - Included in Sub-Metering
18 | Step down transformers |  | EA | 0 | 0 | Excluded
19 | Surge suppressions |  | EA | 0 | 0 | Excluded
20 | Site pole lighting |  | EA | 0 | 0 | Excluded
21 | Lighting control |  | EA | 0 | 0 | Hi-Tech Electric - Included In electrical cost
22 | Specialty wiring & controls |  | EA | 0 | 0 | Hi-Tech Electric - Included In electrical cost
23 | Egress/emergency lighting |  | EA | 0 | 0 | Hi-Tech Electric - Included In electrical cost
16 - Electrical |  |  |  |  | 1398698.78
DIRECT COSTS - TOTAL |  |  |  |  | 18149881.4522
Note on G30: Douglas Kopel: Take 50k

## SOV
PROJECT - SCHEDULE OF VALUES
PROJECT INFORMATION
OWNER | 0
ADDRESS | 725 Santa Fe
DESCRIPTION | 56 Unit Condos
SOV SUMMARY |  | AFP BREAKDOWN | [5 empty] | CHANGE ORDERS
COST CODE | AMOUNT | APP 1 | APP 2 | APP 3 | APP 4 | APP 5 | Total To-Date | % ORIGINAL ESTIMATE | CHANGE ORDERS | REVISED SOV w/ CHANGE ORDERS | DIFFERENCE
00-100 ¦ Permit Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
00-150 ¦ Insurance | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
00-200 ¦ Architecture / Engineering / Design Provided by Others | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
00-300 ¦ Contingency | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
00-400 ¦ Overhead & Profit | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
00-500 ¦ Agreement / Legal Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
01-101 ¦ Project Supervision | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
01-102 ¦ General Labor / Materials / Floor Protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
01-104 ¦ Architecture / Engineering / Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
01-300 ¦ Safety | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
01‐400 ¦ Testing / Surveying / Inspections | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
01-500 ¦ Temporary Facilities / Controls / Chemical Toilets / Fencing | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
01-600 ¦ Rental Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
01-800 ¦ Punch List | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
01-900 ¦ Site / Final Cleaning | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
02-100 ¦ Site Remediation / Demolition / Abatement | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
02-150 ¦ Dumpster / Trash Removal | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
02-201 ¦ Shoring | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
02-300 ¦ Earthwork / Site Preparation | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
02-500 ¦ Utilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
02-600 ¦ Erosion Control / BMP | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
02-800 ¦ Site Improvements / Amenities | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
02-900 ¦ Landscaping / Permanent Fencing | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
03-100 ¦ Foundation | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
03‐500 ¦ Flatwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
03‐900 ¦ Concrete Finishings / Sealing / Cleaning / Striping | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
04-100 ¦ Masonry / Stone | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
05-100 ¦ Structural Metal | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
05-700 ¦ Ornamental Metal | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
06-100 ¦ Rough Carpentry | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
06-200 ¦ Finish Carpentry | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
07-100 ¦ Dampproofing / Waterproofing / Perimeter Drain | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
07-200 ¦ Insulation | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
07-205 ¦ Stucco | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
07-300 ¦ Roofing | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
07-400 ¦ Architectural Metal Panels | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
07-600 ¦ Flashing / Gutters | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
07-900 ¦ Joint Sealers / Draft Stop | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
08-204 ¦ Interior Doors | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
08-205 ¦ Exterior Doors | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
08-206 ¦ Garage Doors | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
08-400 ¦ Storefront / Glazing | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
08-500 ¦ Windows | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
08-700 ¦ Hardware | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
09-100 ¦ Acoustical Ceiling | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
09-200 ¦ Drywall | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
09-300 ¦ Tile | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
09-601 ¦ Hardwood | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
09-602 ¦ Carpet | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
09-700 ¦ Wall Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
09-701 ¦ Cabinets | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
09-702 ¦ Counter Tops | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
09-900 ¦ Paints / Coatings | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
10-150 ¦ Compartments / Cubicles / Lockers / Partitions | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
10-300 ¦ Fireplaces | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
10-350 ¦ Miscellaneous Specialities | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
10-520 ¦ Fire Extinguishers | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
10-550 ¦ Mail Boxes / Signage | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
10-800 ¦ Bath Accessories | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
11-450 ¦ Appliances | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
11-690 ¦ Other Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
12-400 ¦ Furnishings & Accessories | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
13-170 ¦ Tubs / Pools | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
13-800 ¦ Building Automation / Security | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
13-850 ¦ Detection / Alarm / Fire Alarm | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
13-900 ¦ Fire Sprinklers | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
14-200 ¦ Elevators | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
14-600 ¦ Hoists / Cranes / Lifts | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  | 0%
14-800 ¦ Scaffolding | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  | 0%
15-050 ¦ Plumbing | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  | 0%
15-400 ¦ Plumbing Fixtures | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  | 0%
15-401 ¦ Tap Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  | 0%
15-705 ¦ HVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  | 0%
16-200 ¦ Electrical Service / Trim | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  | 0%
16-400 ¦ Low-Voltage Lighting / Audio / Data | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
16-500 ¦ Lighting Fixtures | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
16-700 ¦ Security | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0%
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0

## Project Ledger (hidden)
PROJECT COST LEDGER
PROJECT INFORMATION
Owner: |  |  |  |  | 0
Address: |  |  |  |  | 725 Santa Fe
Description: |  |  |  |  | 56 Unit Condos
# | DATE | TRANSACTION TYPE | INV # | NAME | DESCRIPTION | ACCOUNT | AMOUNT | COST CODE | NOTES/SPLIT | PAY TO | AFP | TYPE
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996

## Change Orders - Summary (hidden)
CHANGE ORDERS: SUMMARY
|  | OWNER: | 0
|  | ADDRESS: | 725 Santa Fe
100 Kalamath St. |  | DESCRIPTION: | 56 Unit Condos
Denver CO, 80223
DATE | # | AMOUNT | DESRIPTION
4310500% | 1 | #VALUE! | 1
4310200% | 2 | #VALUE! | 2
4310300% | 3 | #VALUE! | 3
4310400% | 4 | #VALUE! | 4
4310500% | 5 | #VALUE! | 5
4310600% | 6 | #VALUE! | 6
4310700% | 7 | #VALUE! | 7
4310800% | 8 | #VALUE! | 8
4310900% | 9 | #VALUE! | 9
4311000% | 10 | #VALUE! | 10
TOTAL: CHANGE ORDERS |  | #VALUE!
TOTAL: ORIGINAL CONTRACT SUM |  | 19556497.2648
TOTAL: REVISED CONTRACT SUM |  | #VALUE!

## Change Orders - Detail (hidden)
CHANGE ORDERS: DETAIL
|  |  |  | OWNER: | 0
|  |  |  | ADDRESS: | 725 Santa Fe
100 Kalamath St. |  |  |  | DESCRIPTION: | 56 Unit Condos
Denver CO, 80223
GENERAL PROJECT INFORMATION
|  |  |  | ORIGINAL CONTRACT SUM | 19556497.2648
|  |  |  | ORIGINAL COMPLETION DATE | 2018-01-23
|  |  |  | PM HOURS BUDGETED PER WEEK | 7
|  |  |  | SUPER HOURS BUDGETED PER WEEK | 14
|  |  |  | PM HOURLY RATE | 85
|  |  |  | SUPER HOURLY RATE | 65
|  |  |  | ARCHITECTURE HOURLY RATE | 95
|  |  |  | DESIGN HOURLY RATE | 65
CHANGE ORDER FORM
|  |  |  | DATE | 2018-01-05
100 Kalamath St. |  |  |  | CHANGE ORDER # | 1
Denver CO 80223
This Change Order affects the Contractual Agreement between Denver Design Build, LLC and the Client referenced below, pursuant to section 2.3 of the aforementioned agreement.
PROJECT INFORMATION: | 56 Unit Condos
0
725 Santa Fe
CHANGE ORDER #1: DESCRIPTION
1
CHANGE ORDER #1: COST
ITEM | QTY | UNIT | COST | TOTAL | COST CODE
MANAGEMENT TIME - For C/O Creation/Execution | 0 | EA | 85 | 0 | 01-101 - Project Supervision
Architecture | 0 | EA | 95 | 0 | 01-104 - Architecture / Engineering / Design
Design | 0 | EA | 65 | 0 | 01-104 - Architecture / Engineering / Design
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Site Super Hours Increase - Per Schedule Delay | 14 | EA | 85 | 1190 | 01-101 - Project Supervision
Project Manager Hours increase - Per Schedule Delay | 7 | EA | 65 | 455 | 01-101 - Project Supervision
Subtotal |  |  |  | 1645
|  |  | Insurance | #VALUE! | 00-150 - Insurance
|  |  | Contingency | #REF! | 00-300 - Contingency
|  |  | Overhead and Profit | 33.5714 | 00-400 - Overhead & Profit
Change Order #1 Total |  |  |  | #VALUE!
Orignial Contracted Total |  |  |  | 19556497.2648
Total of Previous Change Orders |  |  |  | 0
|  |  | Original Contract price increased by this Change Order in the Amount of | #VALUE!
New Contracted Total (After this Change Order) |  |  |  | #VALUE!
|  |  | Original Completion Date | 2018-01-23
|  |  | Completion Date Per Previous Change Order | 2018-01-23
|  |  | Total Schedule Delay Days (Excludes Weekends and Holidays) | 5
|  |  | New Completion Date | 2018-01-30
CHANGE ORDER #1: APPROVAL
OWNER SIGNATURE** | DATE |  | CONTRACTOR SIGNATURE** |  | DATE
Hard Cost Change Order
Mandatory Change Order pursuant to§2.7 & §10.1 et. al. of the Construction Agreement
Estimated Cost Change Order*
*Estimated Change Orders are an estimation of the cost of work. Actual cost may vary from the change order |  |  |  |  | Check one of the above
**All Change Orders must be signed and must be paid in full before work described above will commence.
CHANGE ORDER FORM
|  |  |  | DATE | 2018-01-02
100 Kalamath St. |  |  |  | CHANGE ORDER # | 2
Denver CO 80223
This Change Order affects the Contractual Agreement between Denver Design Build, LLC and the Client referenced below, pursuant to section 2.3 of the aforementioned agreement.
PROJECT INFORMATION: | 56 Unit Condos
0
725 Santa Fe
CHANGE ORDER #2: DESCRIPTION
2
CHANGE ORDER #2: COST
ITEM | QTY | UNIT | COST | TOTAL | COST CODE
MANAGEMENT TIME - For C/O Creation/Execution | 0 | EA | 85 | 0 | 01-101 - Project Supervision
Architecture | 0 | EA | 95 | 0 | 01-104 - Architecture / Engineering / Design
Design | 0 | EA | 65 | 0 | 01-104 - Architecture / Engineering / Design
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Site Super Hours Increase - Per Schedule Delay | 5.6 | EA | 85 | 476 | 01-101 - Project Supervision
Project Manager Hours increase - Per Schedule Delay | 2.8 | EA | 65 | 182 | 01-101 - Project Supervision
Subtotal |  |  |  | 658
|  |  | Insurance | #VALUE! | 00-150 - Insurance
|  |  | Contingency | #REF! | 00-300 - Contingency
|  |  | Overhead and Profit | 13.4286 | 00-400 - Overhead & Profit
Change Order #2 Total |  |  |  | #VALUE!
Orignial Contracted Total |  |  |  | 19556497.2648
Total of Previous Change Orders |  |  |  | #VALUE!
|  |  | Original Contract price increased by this Change Order in the Amount of | #VALUE!
New Contracted Total (After this Change Order) |  |  |  | #VALUE!
|  |  | Original Completion Date | 2018-01-23
|  |  | Completion Date Per Previous Change Order | 2018-01-30
|  |  | Total Schedule Delay Days (Excludes Weekends and Holidays) | 2
|  |  | New Completion Date | 2018-02-01
CHANGE ORDER #2: APPROVAL
OWNER SIGNATURE** | DATE |  | CONTRACTOR SIGNATURE** |  | DATE
Hard Cost Change Order
Mandatory Change Order pursuant to§2.7 & §10.1 et. al. of the Construction Agreement
Estimated Cost Change Order*
*Estimated Change Orders are an estimation of the cost of work. Actual cost may vary from the change order |  |  |  |  | Check one of the above
**All Change Orders must be signed and must be paid in full before work described above will commence.
CHANGE ORDER FORM
|  |  |  | DATE | 2018-01-03
100 Kalamath St. |  |  |  | CHANGE ORDER # | 3
Denver CO 80223
This Change Order affects the Contractual Agreement between Denver Design Build, LLC and the Client referenced below, pursuant to section 2.3 of the aforementioned agreement.
PROJECT INFORMATION: | 56 Unit Condos
0
725 Santa Fe
CHANGE ORDER #3: DESCRIPTION
3
CHANGE ORDER #3: COST
ITEM | QTY | UNIT | COST | TOTAL | COST CODE
MANAGEMENT TIME - For C/O Creation/Execution | 0 | EA | 85 | 0 | 01-101 - Project Supervision
Architecture | 0 | EA | 95 | 0 | 01-104 - Architecture / Engineering / Design
Design | 0 | EA | 65 | 0 | 01-104 - Architecture / Engineering / Design
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Site Super Hours Increase - Per Schedule Delay | 16.8 | EA | 85 | 1428 | 01-101 - Project Supervision
Project Manager Hours increase - Per Schedule Delay | 8.4 | EA | 65 | 546 | 01-101 - Project Supervision
Subtotal |  |  |  | 1974
|  |  | Insurance | #VALUE! | 00-150 - Insurance
|  |  | Contingency | #REF! | 00-300 - Contingency
|  |  | Overhead and Profit | 40.2857 | 00-400 - Overhead & Profit
Change Order #3 Total |  |  |  | #VALUE!
Orignial Contracted Total |  |  |  | 19556497.2648
Total of Previous Change Orders |  |  |  | #VALUE!
|  |  | Original Contract price increased by this Change Order in the Amount of | #VALUE!
New Contracted Total (After this Change Order) |  |  |  | #VALUE!
|  |  | Original Completion Date | 2018-01-23
|  |  | Completion Date Per Previous Change Order | 2018-02-01
|  |  | Total Schedule Delay Days (Excludes Weekends and Holidays) | 6
|  |  | New Completion Date | 2018-02-09
CHANGE ORDER #3: APPROVAL
OWNER SIGNATURE** | DATE |  | CONTRACTOR SIGNATURE** |  | DATE
Hard Cost Change Order
Mandatory Change Order pursuant to§2.7 & §10.1 et. al. of the Construction Agreement
Estimated Cost Change Order*
*Estimated Change Orders are an estimation of the cost of work. Actual cost may vary from the change order |  |  |  |  | Check one of the above
**All Change Orders must be signed and must be paid in full before work described above will commence.
CHANGE ORDER FORM
|  |  |  | DATE | 2018-01-04
100 Kalamath St. |  |  |  | CHANGE ORDER # | 4
Denver CO 80223
This Change Order affects the Contractual Agreement between Denver Design Build, LLC and the Client referenced below, pursuant to section 2.3 of the aforementioned agreement.
PROJECT INFORMATION: | 56 Unit Condos
0
725 Santa Fe
CHANGE ORDER #4: DESCRIPTION
4
CHANGE ORDER #4: COST
ITEM | QTY | UNIT | COST | TOTAL | COST CODE
MANAGEMENT TIME - For C/O Creation/Execution | 0 | EA | 85 | 0 | 01-101 - Project Supervision
Architecture | 0 | EA | 95 | 0 | 01-104 - Architecture / Engineering / Design
Design | 0 | EA | 65 | 0 | 01-104 - Architecture / Engineering / Design
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Site Super Hours Increase - Per Schedule Delay | 11.2 | EA | 85 | 952 | 01-101 - Project Supervision
Project Manager Hours increase - Per Schedule Delay | 5.6 | EA | 65 | 364 | 01-101 - Project Supervision
Subtotal |  |  |  | 1316
|  |  | Insurance | #VALUE! | 00-150 - Insurance
|  |  | Contingency | #REF! | 00-300 - Contingency
|  |  | Overhead and Profit | 26.8571 | 00-400 - Overhead & Profit
Change Order #4 Total |  |  |  | #VALUE!
Orignial Contracted Total |  |  |  | 19556497.2648
Total of Previous Change Orders |  |  |  | #VALUE!
|  |  | Original Contract price increased by this Change Order in the Amount of | #VALUE!
New Contracted Total (After this Change Order) |  |  |  | #VALUE!
|  |  | Original Completion Date | 2018-01-23
|  |  | Completion Date Per Previous Change Order | 2018-02-09
|  |  | Total Schedule Delay Days (Excludes Weekends and Holidays) | 4
|  |  | New Completion Date | 2018-02-15
CHANGE ORDER #4: APPROVAL
OWNER SIGNATURE** | DATE |  | CONTRACTOR SIGNATURE** |  | DATE
Hard Cost Change Order
Mandatory Change Order pursuant to§2.7 & §10.1 et. al. of the Construction Agreement
Estimated Cost Change Order*
*Estimated Change Orders are an estimation of the cost of work. Actual cost may vary from the change order |  |  |  |  | Check one of the above
**All Change Orders must be signed and must be paid in full before work described above will commence.
CHANGE ORDER FORM
|  |  |  | DATE | 2018-01-05
100 Kalamath St. |  |  |  | CHANGE ORDER # | 5
Denver CO 80223
This Change Order affects the Contractual Agreement between Denver Design Build, LLC and the Client referenced below, pursuant to section 2.3 of the aforementioned agreement.
PROJECT INFORMATION: | 56 Unit Condos
0
725 Santa Fe
CHANGE ORDER #5: DESCRIPTION
5
CHANGE ORDER #5: COST
ITEM | QTY | UNIT | COST | TOTAL | COST CODE
MANAGEMENT TIME - For C/O Creation/Execution | 0 | EA | 85 | 0 | 01-101 - Project Supervision
Architecture | 0 | EA | 95 | 0 | 01-104 - Architecture / Engineering / Design
Design | 0 | EA | 65 | 0 | 01-104 - Architecture / Engineering / Design
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Site Super Hours Increase - Per Schedule Delay | 14 | EA | 85 | 1190 | 01-101 - Project Supervision
Project Manager Hours increase - Per Schedule Delay | 7 | EA | 65 | 455 | 01-101 - Project Supervision
Subtotal |  |  |  | 1645
|  |  | Insurance | #VALUE! | 00-150 - Insurance
|  |  | Contingency | #REF! | 00-300 - Contingency
|  |  | Overhead and Profit | 33.5714 | 00-400 - Overhead & Profit
Change Order #5 Total |  |  |  | #VALUE!
Orignial Contracted Total |  |  |  | 19556497.2648
Total of Previous Change Orders |  |  |  | #VALUE!
|  |  | Original Contract price increased by this Change Order in the Amount of | #VALUE!
New Contracted Total (After this Change Order) |  |  |  | #VALUE!
|  |  | Original Completion Date | 2018-01-23
|  |  | Completion Date Per Previous Change Order | 2018-02-15
|  |  | Total Schedule Delay Days (Excludes Weekends and Holidays) | 5
|  |  | New Completion Date | 2018-02-22
CHANGE ORDER #5: APPROVAL
OWNER SIGNATURE** | DATE |  | CONTRACTOR SIGNATURE** |  | DATE
Hard Cost Change Order
Mandatory Change Order pursuant to§2.7 & §10.1 et. al. of the Construction Agreement
Estimated Cost Change Order*
*Estimated Change Orders are an estimation of the cost of work. Actual cost may vary from the change order |  |  |  |  | Check one of the above
**All Change Orders must be signed and must be paid in full before work described above will commence.
CHANGE ORDER FORM
|  |  |  | DATE | 2018-01-06
100 Kalamath St. |  |  |  | CHANGE ORDER # | 6
Denver CO 80223
This Change Order affects the Contractual Agreement between Denver Design Build, LLC and the Client referenced below, pursuant to section 2.3 of the aforementioned agreement.
PROJECT INFORMATION: | 56 Unit Condos
0
725 Santa Fe
CHANGE ORDER #6: DESCRIPTION
6
CHANGE ORDER #6: COST
ITEM | QTY | UNIT | COST | TOTAL | COST CODE
MANAGEMENT TIME - For C/O Creation/Execution | 0 | EA | 85 | 0 | 01-101 - Project Supervision
Architecture | 0 | EA | 95 | 0 | 01-104 - Architecture / Engineering / Design
Design | 0 | EA | 65 | 0 | 01-104 - Architecture / Engineering / Design
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Site Super Hours Increase - Per Schedule Delay | 16.8 | EA | 85 | 1428 | 01-101 - Project Supervision
Project Manager Hours increase - Per Schedule Delay | 8.4 | EA | 65 | 546 | 01-101 - Project Supervision
Subtotal |  |  |  | 1974
|  |  | Insurance | #VALUE! | 00-150 - Insurance
|  |  | Contingency | #REF! | 00-300 - Contingency
|  |  | Overhead and Profit | 40.2857 | 00-400 - Overhead & Profit
Change Order #6 Total |  |  |  | #VALUE!
Orignial Contracted Total |  |  |  | 19556497.2648
Total of Previous Change Orders |  |  |  | #VALUE!
|  |  | Original Contract price increased by this Change Order in the Amount of | #VALUE!
New Contracted Total (After this Change Order) |  |  |  | #VALUE!
|  |  | Original Completion Date | 2018-01-23
|  |  | Completion Date Per Previous Change Order | 2018-02-22
|  |  | Total Schedule Delay Days (Excludes Weekends and Holidays) | 6
|  |  | New Completion Date | 2018-03-02
CHANGE ORDER #6: APPROVAL
OWNER SIGNATURE** | DATE |  | CONTRACTOR SIGNATURE** |  | DATE
Hard Cost Change Order
Mandatory Change Order pursuant to§2.7 & §10.1 et. al. of the Construction Agreement
Estimated Cost Change Order*
*Estimated Change Orders are an estimation of the cost of work. Actual cost may vary from the change order |  |  |  |  | Check one of the above
**All Change Orders must be signed and must be paid in full before work described above will commence.
CHANGE ORDER FORM
|  |  |  | DATE | 2018-01-07
100 Kalamath St. |  |  |  | CHANGE ORDER # | 7
Denver CO 80223
This Change Order affects the Contractual Agreement between Denver Design Build, LLC and the Client referenced below, pursuant to section 2.3 of the aforementioned agreement.
PROJECT INFORMATION: | 56 Unit Condos
0
725 Santa Fe
CHANGE ORDER #7: DESCRIPTION
7
CHANGE ORDER #7: COST
ITEM | QTY | UNIT | COST | TOTAL | COST CODE
MANAGEMENT TIME - For C/O Creation/Execution | 0 | EA | 85 | 0 | 01-101 - Project Supervision
Architecture | 0 | EA | 95 | 0 | 01-104 - Architecture / Engineering / Design
Design | 0 | EA | 65 | 0 | 01-104 - Architecture / Engineering / Design
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Site Super Hours Increase - Per Schedule Delay | 19.6 | EA | 85 | 1666 | 01-101 - Project Supervision
Project Manager Hours increase - Per Schedule Delay | 9.8 | EA | 65 | 637 | 01-101 - Project Supervision
Subtotal |  |  |  | 2303
|  |  | Insurance | #VALUE! | 00-150 - Insurance
|  |  | Contingency | #REF! | 00-300 - Contingency
|  |  | Overhead and Profit | 47 | 00-400 - Overhead & Profit
Change Order #7 Total |  |  |  | #VALUE!
Orignial Contracted Total |  |  |  | 19556497.2648
Total of Previous Change Orders |  |  |  | #VALUE!
|  |  | Original Contract price increased by this Change Order in the Amount of | #VALUE!
New Contracted Total (After this Change Order) |  |  |  | #VALUE!
|  |  | Original Completion Date | 2018-01-23
|  |  | Completion Date Per Previous Change Order | 2018-03-02
|  |  | Total Schedule Delay Days (Excludes Weekends and Holidays) | 7
|  |  | New Completion Date | 2018-03-13
CHANGE ORDER #7: APPROVAL
OWNER SIGNATURE** | DATE |  | CONTRACTOR SIGNATURE** |  | DATE
Hard Cost Change Order
Mandatory Change Order pursuant to§2.7 & §10.1 et. al. of the Construction Agreement
Estimated Cost Change Order*
*Estimated Change Orders are an estimation of the cost of work. Actual cost may vary from the change order |  |  |  |  | Check one of the above
**All Change Orders must be signed and must be paid in full before work described above will commence.
CHANGE ORDER FORM
|  |  |  | DATE | 2018-01-08
100 Kalamath St. |  |  |  | CHANGE ORDER # | 8
Denver CO 80223
This Change Order affects the Contractual Agreement between Denver Design Build, LLC and the Client referenced below, pursuant to section 2.3 of the aforementioned agreement.
PROJECT INFORMATION: | 56 Unit Condos
0
725 Santa Fe
CHANGE ORDER #8: DESCRIPTION
8
CHANGE ORDER #8: COST
ITEM | QTY | UNIT | COST | TOTAL | COST CODE
MANAGEMENT TIME - For C/O Creation/Execution | 0 | EA | 85 | 0 | 01-101 - Project Supervision
Architecture | 0 | EA | 95 | 0 | 01-104 - Architecture / Engineering / Design
Design | 0 | EA | 65 | 0 | 01-104 - Architecture / Engineering / Design
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Site Super Hours Increase - Per Schedule Delay | 22.4 | EA | 85 | 1904 | 01-101 - Project Supervision
Project Manager Hours increase - Per Schedule Delay | 11.2 | EA | 65 | 728 | 01-101 - Project Supervision
Subtotal |  |  |  | 2632
|  |  | Insurance | #VALUE! | 00-150 - Insurance
|  |  | Contingency | #REF! | 00-300 - Contingency
|  |  | Overhead and Profit | 53.7143 | 00-400 - Overhead & Profit
Change Order #8 Total |  |  |  | #VALUE!
Orignial Contracted Total |  |  |  | 19556497.2648
Total of Previous Change Orders |  |  |  | #VALUE!
|  |  | Original Contract price increased by this Change Order in the Amount of | #VALUE!
New Contracted Total (After this Change Order) |  |  |  | #VALUE!
|  |  | Original Completion Date | 2018-01-23
|  |  | Completion Date Per Previous Change Order | 2018-03-13
|  |  | Total Schedule Delay Days (Excludes Weekends and Holidays) | 8
|  |  | New Completion Date | 2018-03-23
CHANGE ORDER #8: APPROVAL
OWNER SIGNATURE** | DATE |  | CONTRACTOR SIGNATURE** |  | DATE
Hard Cost Change Order
Mandatory Change Order pursuant to§2.7 & §10.1 et. al. of the Construction Agreement
Estimated Cost Change Order*
*Estimated Change Orders are an estimation of the cost of work. Actual cost may vary from the change order |  |  |  |  | Check one of the above
**All Change Orders must be signed and must be paid in full before work described above will commence.
CHANGE ORDER FORM
|  |  |  | DATE | 2018-01-09
100 Kalamath St. |  |  |  | CHANGE ORDER # | 9
Denver CO 80223
This Change Order affects the Contractual Agreement between Denver Design Build, LLC and the Client referenced below, pursuant to section 2.3 of the aforementioned agreement.
PROJECT INFORMATION: | 56 Unit Condos
0
725 Santa Fe
CHANGE ORDER #9: DESCRIPTION
9
CHANGE ORDER #9: COST
ITEM | QTY | UNIT | COST | TOTAL | COST CODE
MANAGEMENT TIME - For C/O Creation/Execution | 0 | EA | 85 | 0 | 01-101 - Project Supervision
Architecture | 0 | EA | 95 | 0 | 01-104 - Architecture / Engineering / Design
Design | 0 | EA | 65 | 0 | 01-104 - Architecture / Engineering / Design
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Site Super Hours Increase - Per Schedule Delay | 25.2 | EA | 85 | 2142 | 01-101 - Project Supervision
Project Manager Hours increase - Per Schedule Delay | 12.6 | EA | 65 | 819 | 01-101 - Project Supervision
Subtotal |  |  |  | 2961
|  |  | Insurance | #VALUE! | 00-150 - Insurance
|  |  | Contingency | #REF! | 00-300 - Contingency
|  |  | Overhead and Profit | 60.4286 | 00-400 - Overhead & Profit
Change Order #9 Total |  |  |  | #VALUE!
Orignial Contracted Total |  |  |  | 19556497.2648
Total of Previous Change Orders |  |  |  | #VALUE!
|  |  | Original Contract price increased by this Change Order in the Amount of | #VALUE!
New Contracted Total (After this Change Order) |  |  |  | #VALUE!
|  |  | Original Completion Date | 2018-01-23
|  |  | Completion Date Per Previous Change Order | 2018-03-23
|  |  | Total Schedule Delay Days (Excludes Weekends and Holidays) | 9
|  |  | New Completion Date | 2018-04-05
CHANGE ORDER #9: APPROVAL
OWNER SIGNATURE** | DATE |  | CONTRACTOR SIGNATURE** |  | DATE
Hard Cost Change Order
Mandatory Change Order pursuant to§2.7 & §10.1 et. al. of the Construction Agreement
Estimated Cost Change Order*
*Estimated Change Orders are an estimation of the cost of work. Actual cost may vary from the change order |  |  |  |  | Check one of the above
**All Change Orders must be signed and must be paid in full before work described above will commence.
CHANGE ORDER FORM
|  |  |  | DATE | 2018-01-10
100 Kalamath St. |  |  |  | CHANGE ORDER # | 10
Denver CO 80223
This Change Order affects the Contractual Agreement between Denver Design Build, LLC and the Client referenced below, pursuant to section 2.3 of the aforementioned agreement.
PROJECT INFORMATION: | 56 Unit Condos
0
725 Santa Fe
CHANGE ORDER #10: DESCRIPTION
10
CHANGE ORDER #10: COST
ITEM | QTY | UNIT | COST | TOTAL | COST CODE
MANAGEMENT TIME - For C/O Creation/Execution | 0 | EA | 85 | 0 | 01-101 - Project Supervision
Architecture | 0 | EA | 95 | 0 | 01-104 - Architecture / Engineering / Design
Design | 0 | EA | 65 | 0 | 01-104 - Architecture / Engineering / Design
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Site Super Hours Increase - Per Schedule Delay | 28 | EA | 85 | 2380 | 01-101 - Project Supervision
Project Manager Hours increase - Per Schedule Delay | 14 | EA | 65 | 910 | 01-101 - Project Supervision
Subtotal |  |  |  | 3290
|  |  | Insurance | #VALUE! | 00-150 - Insurance
|  |  | Contingency | #REF! | 00-300 - Contingency
|  |  | Overhead and Profit | 67.1429 | 00-400 - Overhead & Profit
Change Order #10 Total |  |  |  | #VALUE!
Orignial Contracted Total |  |  |  | 19556497.2648
Total of Previous Change Orders |  |  |  | #VALUE!
|  |  | Original Contract price increased by this Change Order in the Amount of | #VALUE!
New Contracted Total (After this Change Order) |  |  |  | #VALUE!
|  |  | Original Completion Date | 2018-01-23
|  |  | Completion Date Per Previous Change Order | 2018-04-05
|  |  | Total Schedule Delay Days (Excludes Weekends and Holidays) | 10
|  |  | New Completion Date | 2018-04-19
CHANGE ORDER #10: APPROVAL
OWNER SIGNATURE** | DATE |  | CONTRACTOR SIGNATURE** |  | DATE
Hard Cost Change Order
Mandatory Change Order pursuant to§2.7 & §10.1 et. al. of the Construction Agreement
Estimated Cost Change Order*
*Estimated Change Orders are an estimation of the cost of work. Actual cost may vary from the change order |  |  |  |  | Check one of the above
**All Change Orders must be signed and must be paid in full before work described above will commence.

## Payments (hidden)
PAYMENTS TO DATE
| OWNER | 0
| ADDRESS | 725 Santa Fe
| DESCRIPTION | 56 Unit Condos
# | DATE | TRANSACTION TYPE | INVOICE # | NAME | MEMO/DESCRIPTION | SPLIT | AMOUNT | TYPE
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
[6 empty] | Construction Contract | 0 | TOTAL RECEIVED
[6 empty] | Design Contract | 0 | TOTAL RECEIVED
[6 empty] | ORIGINAL ESTIMATE (CONSTRUCTION CONTRACT) | 19556497.2648
[6 empty] | CHANGE ORDERS | #VALUE!
[6 empty] | REVISED CONTRACT WITH CHANGE ORDERS | #VALUE!
CONSTRUCTION PAYMENTS TO DATE
CONSTRUCTION BALANCE TO FINISH
ConstructionPaymentsReceived

## PROJECT SOV LIST (hidden)
MASTER SOV
# | COST CODE | AMOUNT
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## DATA (hidden)
Cost Code Selection Lists |  |  |  | IncrementBy | 1 | AFP | MASTER COST CODE LIST
ContractingRequirementsList |  | Division Lookup |  | StartAt | 1 | App 1 | 00-100 ¦ Permit Fee
00-100 ¦ Permit Fee |  | 00 - Contracting Requirements | ContractingRequirements |  |  | App 2 | 00-150 ¦ Insurance
00-150 ¦ Insurance |  | 01 - General Requirements | GeneralRequirements | PaymentType |  | App 3 | 00-200 ¦ Architecture / Engineering / Design Provided by Others
00-200 ¦ Architecture / Engineering / Design Provided by Others |  | 02 - Site Construction | SiteConstruction | Design Contract |  | App 4 | 00-300 ¦ Contingency
00-300 ¦ Contingency |  | 03 - Concrete | Concrete | Construction Contract |  | App 5 | 00-400 ¦ Overhead & Profit
00-400 ¦ Overhead & Profit |  | 04 - Masonry | Masonry |  |  | App 6 | 00-500 ¦ Agreement / Legal Services
00-500 ¦ Agreement / Legal Services |  | 05 - Metals | Metals |  |  | App 7 | 01-101 ¦ Project Supervision
GeneralRequirementsList |  | 06 - Wood & Plastics | WoodPlastic |  |  | App 8 | 01-102 ¦ General Labor / Materials / Floor Protection
01-101 ¦ Project Supervision |  | 07 - Thermal & Moisture Protection | ThermalMoisture |  |  | App 9 | 01-104 ¦ Architecture / Engineering / Design
01-102 ¦ General Labor / Materials / Floor Protection |  | 08 - Doors & Windows | DoorsWindows |  |  | App 10 | 01-300 ¦ Safety
01-104 ¦ Architecture / Engineering / Design |  | 09 - Finishes | Finishes |  |  | App 11 | 01‐400 ¦ Testing / Surveying / Inspections
01-300 ¦ Safety |  | 10 - Specialties | Specialties |  |  | App 12 | 01-500 ¦ Temporary Facilities / Controls / Chemical Toilets / Fencing
01‐400 ¦ Testing / Surveying / Inspections |  | 11 - Equipment | Equipment |  |  | App 13 | 01-600 ¦ Rental Equipment
01-500 ¦ Temporary Facilities / Controls / Chemical Toilets / Fencing |  | 12 - Furnishings | Furnishings |  |  | App 14 | 01-800 ¦ Punch List
01-600 ¦ Rental Equipment |  | 13 - Specialty Construction | SpecialtyConstruction |  |  | App 15 | 01-900 ¦ Site / Final Cleaning
01-800 ¦ Punch List |  | 14 - Conveying Systems | ConveyingSystems | LaborType |  | App 16 | 02-100 ¦ Site Remediation / Demolition / Abatement
01-900 ¦ Site / Final Cleaning |  | 15 - Mechanical | Mechanical | PM |  | App 17 | 02-150 ¦ Dumpster / Trash Removal
|  | 16 - Electrical | Electrical | Carpenter |  | App 18 | 02-201 ¦ Shoring
SiteConstructionList |  |  |  | Laborer |  | App 19 | 02-300 ¦ Earthwork / Site Preparation
02-100 ¦ Site Remediation / Demolition / Abatement |  |  |  | Design |  | App 20 | 02-500 ¦ Utilities
02-150 ¦ Dumpster / Trash Removal |  |  |  | Other |  | App 21 | 02-600 ¦ Erosion Control / BMP
02-201 ¦ Shoring | [5 empty] | App 22 | 02-800 ¦ Site Improvements / Amenities
02-300 ¦ Earthwork / Site Preparation | [5 empty] | App 23 | 02-900 ¦ Landscaping / Permanent Fencing
02-500 ¦ Utilities | [5 empty] | App 24 | 03-100 ¦ Foundation
02-600 ¦ Erosion Control / BMP | [5 empty] | App 25 | 03‐500 ¦ Flatwork
02-800 ¦ Site Improvements / Amenities | [5 empty] | App 26 | 03‐900 ¦ Concrete Finishings / Sealing / Cleaning / Striping
02-900 ¦ Landscaping / Permanent Fencing | [5 empty] | App 27 | 04-100 ¦ Masonry / Stone
ConcreteList | [5 empty] | App 28 | 05-100 ¦ Structural Metal
03-100 ¦ Foundation | [5 empty] | App 29 | 05-700 ¦ Ornamental Metal
03‐500 ¦ Flatwork | [5 empty] | App 30 | 06-100 ¦ Rough Carpentry
03‐900 ¦ Concrete Finishings / Sealing / Cleaning / Striping |  |  |  | TypeList | TypeAbvList |  | 06-200 ¦ Finish Carpentry
MasonryList |  |  |  | Labor | L |  | 07-100 ¦ Dampproofing / Waterproofing / Perimeter Drain
04-100 ¦ Masonry / Stone |  |  |  | Equipment | E |  | 07-200 ¦ Insulation
MetalsList |  |  |  | Materials | M |  | 07-205 ¦ Stucco
05-100 ¦ Structural Metal |  |  |  | Commitment | S |  | 07-300 ¦ Roofing
05-700 ¦ Ornamental Metal |  |  |  | Owner Cost | OC |  | 07-400 ¦ Architectural Metal Panels
WoodPlasticList |  |  |  | Professional Services | SVC |  | 07-600 ¦ Flashing / Gutters
06-100 ¦ Rough Carpentry |  |  |  | Other | O |  | 07-900 ¦ Joint Sealers / Draft Stop
06-200 ¦ Finish Carpentry | [6 empty] | 08-204 ¦ Interior Doors
ThermalMoistureList | [6 empty] | 08-205 ¦ Exterior Doors
07-100 ¦ Dampproofing / Waterproofing / Perimeter Drain | [6 empty] | 08-206 ¦ Garage Doors
07-200 ¦ Insulation | [6 empty] | 08-400 ¦ Storefront / Glazing
07-205 ¦ Stucco | [6 empty] | 08-500 ¦ Windows
07-300 ¦ Roofing | [6 empty] | 08-700 ¦ Hardware
07-400 ¦ Architectural Metal Panels | [6 empty] | 09-100 ¦ Acoustical Ceiling
07-600 ¦ Flashing / Gutters | [6 empty] | 09-200 ¦ Drywall
07-900 ¦ Joint Sealers / Draft Stop | [6 empty] | 09-300 ¦ Tile
DoorsWindowsList | [6 empty] | 09-601 ¦ Hardwood
08-204 ¦ Interior Doors | [6 empty] | 09-602 ¦ Carpet
08-205 ¦ Exterior Doors | [6 empty] | 09-700 ¦ Wall Finishes
08-206 ¦ Garage Doors | [6 empty] | 09-701 ¦ Cabinets
08-400 ¦ Storefront / Glazing | [6 empty] | 09-702 ¦ Counter Tops
08-500 ¦ Windows | [6 empty] | 09-900 ¦ Paints / Coatings
08-700 ¦ Hardware | [6 empty] | 10-150 ¦ Compartments / Cubicles / Lockers / Partitions
FinishesList | [6 empty] | 10-300 ¦ Fireplaces
09-100 ¦ Acoustical Ceiling | [6 empty] | 10-350 ¦ Miscellaneous Specialities
09-200 ¦ Drywall | [6 empty] | 10-520 ¦ Fire Extinguishers
09-300 ¦ Tile | [6 empty] | 10-550 ¦ Mail Boxes / Signage
09-601 ¦ Hardwood | [6 empty] | 10-800 ¦ Bath Accessories
09-602 ¦ Carpet | [6 empty] | 11-450 ¦ Appliances
09-700 ¦ Wall Finishes | [6 empty] | 11-690 ¦ Other Equipment
09-701 ¦ Cabinets | [6 empty] | 12-400 ¦ Furnishings & Accessories
09-702 ¦ Counter Tops | [6 empty] | 13-170 ¦ Tubs / Pools
09-900 ¦ Paints / Coatings | [6 empty] | 13-800 ¦ Building Automation / Security
SpecialtiesList | [6 empty] | 13-850 ¦ Detection / Alarm / Fire Alarm
10-150 ¦ Compartments / Cubicles / Lockers / Partitions | [6 empty] | 13-900 ¦ Fire Sprinklers
10-300 ¦ Fireplaces | [6 empty] | 14-200 ¦ Elevators
10-350 ¦ Miscellaneous Specialities | [6 empty] | 14-600 ¦ Hoists / Cranes / Lifts
10-520 ¦ Fire Extinguishers | [6 empty] | 14-800 ¦ Scaffolding
10-550 ¦ Mail Boxes / Signage | [6 empty] | 15-050 ¦ Plumbing
10-800 ¦ Bath Accessories | [6 empty] | 15-400 ¦ Plumbing Fixtures
EquipmentList | [6 empty] | 15-401 ¦ Tap Fees
11-450 ¦ Appliances | [6 empty] | 15-705 ¦ HVAC
11-690 ¦ Other Equipment | [6 empty] | 16-200 ¦ Electrical Service / Trim
FurnishingsList | [6 empty] | 16-400 ¦ Low-Voltage Lighting / Audio / Data
12-400 ¦ Furnishings & Accessories | [6 empty] | 16-500 ¦ Lighting Fixtures
SpecialConstructionList | [6 empty] | 16-700 ¦ Security
13-170 ¦ Tubs / Pools
13-800 ¦ Building Automation / Security
13-850 ¦ Detection / Alarm / Fire Alarm
13-900 ¦ Fire Sprinklers
ConveryingSystemsList
14-200 ¦ Elevators
14-600 ¦ Hoists / Cranes / Lifts
14-800 ¦ Scaffolding
MechanicalList
15-050 ¦ Plumbing
15-400 ¦ Plumbing Fixtures
15-401 ¦ Tap Fees
15-705 ¦ HVAC
ElectricalList
16-200 ¦ Electrical Service / Trim
16-400 ¦ Low-Voltage Lighting / Audio / Data
16-500 ¦ Lighting Fixtures
16-700 ¦ Security
Holidays
| 2018 | New Years Day | 4310100%
|  | Memorial Day | 4324800%
|  | Indepence Day | 4328500%
|  | Labor Day | 4334600%
|  | Thanksgiving Day | 4342600%
|  | Christmas Day | 4345900%
| 2019 | New Years Day | 4346600%
|  | Memorial Day | 4361200%
|  | Indepence Day | 4365000%
|  | Labor Day | 4371000%
|  | Thanksgiving Day | 4379700%
|  | Christmas Day | 4382400%
| 2020 | New Years Day | 4383100%
|  | Memorial Day | 4397600%
|  | Indepence Day | 4401600%
|  | Labor Day | 4408100%
|  | Thanksgiving Day | 4416100%
|  | Christmas Day | 4419000%
| 2021 | New Years Day | 4419700%
|  | Memorial Day | 4434700%
|  | Indepence Day | 4438100%
|  | Labor Day | 4444500%
|  | Thanksgiving Day | 4452500%
|  | Christmas Day | 4455500%
| 2022 | New Years Day | 4456200%
|  | Memorial Day | 4471100%
|  | Indepence Day | 4474600%
|  | Labor Day | 4480900%
|  | Thanksgiving Day | 4488900%
|  | Christmas Day | 4492000%
| 2023 | New Years Day | 4492700%
|  | Memorial Day | 4507500%
|  | Indepence Day | 4511100%
|  | Labor Day | 4517300%
|  | Thanksgiving Day | 4525300%
|  | Christmas Day | 4528500%
| 2024 | New Years Day | 4529200%
|  | Memorial Day | 4543900%
|  | Indepence Day | 4547700%
|  | Labor Day | 4553700%
|  | Thanksgiving Day | 4562400%
|  | Christmas Day | 4565100%
| 2025 | New Years Day | 4565800%
|  | Memorial Day | 4580300%
|  | Indepence Day | 4584200%
|  | Labor Day | 4590100%
|  | Thanksgiving Day | 4598800%
|  | Christmas Day | 4601600%
| 2026 | New Years Day | 4602300%
|  | Memorial Day | 4616700%
|  | Indepence Day | 4620700%
|  | Labor Day | 4627200%
|  | Thanksgiving Day | 4635200%
|  | Christmas Day | 4638100%
| 2027 | New Years Day | 4638800%
|  | Memorial Day | 4653800%
|  | Indepence Day | 4657200%
|  | Labor Day | 4663400%
|  | Thanksgiving Day | 4671600%
|  | Christmas Day | 4674600%

## Project Inputs
Project inputs |  | Hourly Rates
Number of buildings | 4 | Project Manager | 85
Number of units | 20 | Lead super | 75
Conditioned sf | 25000 | Assistant super/PE | 55
Average unit size |  | Admin/billing | 40
Lot size | 48000 | General labor | 35
Estimated budget | 5000000 | Skilled labor | 40
Number of weeks | 60 | Carpenter | 65
Roof top patios | No
Difficulty of framing | 3
Difficulty of foundation

## Div 1
1 | MANAGEMENT/LABOR
2 | Project manager
3 | Lead superintendent
4 | Assistant superintendent
5 | Project engineer
6 | General labor
7 | Accounting & billing labor
8 | Procore management software
Using .01% of the project cost
9
10 | INSPECTIONS/ WARRANTY/SURVEY
11 | Structural engineering inspections
Allison - Veradyn Engineers - $125/hr, $100 per letter per building. Total $1,100 per building
Julian - Sundance - $5,570
Saola -
Federal - DL Engineer $1,000
12 | Concrete compaction & slump testing
Federal - Martinez - $1,750 for the building. For building only, no driveway
Allison - CTL - $11,395
Julian - Contour - $2,820 - 4 blds, 2 poured at once, no drive compaction or testing
Saola - Contour
13 | Private storm, sewer and water special inspections
Charging 8 hr/day @ $75 per hour or $600 per day
14 | Surveying
Federal - Falcon - $2,000
Alison - Falcon - $19,898 - Driveway, private mains, driveway, retaining wall. No parcel splits
Julian - Falcon - $7,950 - includes parcel split
15 | As-builts
Dahlia - ABCS - $1,500
16 | Warranty service
$1,500 per unit under $400 - $600k
$2,500 per unit $1mil - $2mil
18 | OTHER GENERAL REQUIREMENTS
19 | General materials
By million
20 | Small tools and consumables
By million
21 | Floor protection
$400 per unit. $800 for larger projects
Julian - Pioneer west - $1,800 materials, double for labor $3,600
22 | Sanitary facilities
$350 per toilet
23 | Winter conditions & weather protection
Excluded, bill per occurance
24 | Rain, snow and weed control/removal
$30/wk
25 | Site security - cameras, locks, lighting, misc
$1,500 per project
26 | Internet service and cell phone
$50/wk
27 | Temporary water & power billings
Federal - $50/mo temp power, water $30/mo - Total $80/month per building
28 | Safety supplies, meetings, training & inspections
$1,500 per project
29 | Jobsite office supplies, blueprints, printing & site drinking water
$1,500 per project
30 | Blower door testing
$350/unit
31 | Right of way, street/alley closure permits
Julian - $1,500 to close sidewalk
Vaquita - $2,500 to close alley for 6 months, 80' of alley
32 | Final & window cleaning
$400 per unit for interior and window, $275 hvac blow out
33 | Travel & lodging
34 | Mileage
35 | $100 per month
36 | TEMPORARY EQUIPMENT
37 | Temp fencing and signage
Federal - $200/mo. No install - National & CAM
Condor - $250/mo
DDB signage $400 per project
38 | Office
$400 per month at 60% of the time of project
39 | Storage containers
$125 per storage per month includes delivery. Per each
40 | Scaffolding
Boston - 6 sections $1200 setup & $100/wk
41 | Boom lifts
$1,000 per week includes delivery & pickup
42 | Fork lifts
$1,000 per week includes delivery & pickup
43 | Scissor lifts
$500 per week includes delivery & pickup
44 | Hoisting equipment
45 | Cranes
$300/hr for daily cranes
46 | Misc rentals
Skid steer - $650/wk
47 | Temp generators
$500/Wk for mid range
49 | ARCHITECTURE/ENGINEERING/DESIGN
50 | Architecture
51 | Engineering
52 | Interior design
53 | Asbestos & lead testing
54 | ISP Survey
55 | Geotechnical report (soils)

## Div 2
# | DESCRIPTION
Trash removal - roll off dumpsters
Allison - $12,500. Estimated
Julian - Elite $9,400
Boston - $6,500
Vehicle tracking control
Allison - $2,500 non Denver
Federal $1,000 Denver
1 | BMP, erosion and sediment control
Julian - Dtech - $1,000 initial. Double for maintenance
1 | Building & site demolition
Yates - $22,000 removed O&P
Knox - $50,000 w/ O&P
1 | Tree removal
Yates - $2,000 Light trees and minimal
Knox - $11,000 - very dense and large trees
1 | Hazardous material abatement
Knox - $10,000
1 | Clear & grub site
1 | Excavation & backfill
2 | Over-excavation
3 | Rough grading
4 | Fine grading
5 | Hand excavation & compaction
6 | Structural fill
7 | Trucking - import/export
8 | Shoring
9 | Utility trenching
10 | Temporary construction water
11 | Right of way permits
12 | Fire hydrant
Allison - SWI - $8,500 on site, no street work
Columbine - SWI - $13,500. With traffic control, patch
1 | Sewer lines
2 | Water lines
3 | Caisson drilling
4 | Caisson spoil removal
5 | Temporary access ramps
6 | Underground roof drains
7 | Traffic control
8 | Sawcut & asphalt/concrete removal
9 | Storm sewer, manholes and inlets
10 | Water detention and water quality
11 | Sand & oil interceptor
12 | Septic tanks, leach field
13 | Grease trap
14 | Dewatering
15 | Rip rap
16 | Hydroseed
17 | Landscaping
Julian - Tano - $35,000 no fence or grasscrete, corner lot 200LF
Allison - Cutting Edge $49,000 no fence
1 | Fencing & gates
1 | Trash enclosure
1 | Retaining walls - landscape block
Allison - Cutting Edge - $25/sf. Includes 1' underground
1 | Permanent site signage
1 | Monument signage
2 | Back racks
Columbine - $1,200 for triple rack, no install
1 | Site amenites

## Div 3
# | DESCRIPTION
1 | Foundation - spread footings
2 | Foundation - walls
3 | Foundation - brick ledge or framing ledge
4 | Foundation - cassions
5 | Foundation - cassion casing
6 | Foundation - pad footers
7 | Specialty footings
8 | Concrete columns & pilasters
9 | Dowl & epoxy into existing foundation
10 | Concrete pumping
11 | Hold downs
12 | Structural slab
13 | Concrete retaining walls
14 | Pre-cast concrete walls
15 | Architectural pre-cast concrete
16 | Slab on grade - garage and interior
17 | Slab on grade - drive aisle
18 | Slab on grade - steps
19 | Slab on grade - patios & walkways
20 | Slab on metal deck
21 | ROW sidewalk
22 | ROW curb & gutter
23 | ROW curb
24 | ROW drive apron
25 | Handicap ramps
26 | Concrete bumpers
27 | Concrete for pan stairs
28 | Trickle channel/drain pan
29 | Light pole bases
30 | Bollards
31 | Trench drain
32 | Post tension slabs
33 | Mono slab w/ 18" turndown
34 | Gyp-crete/light weight concrete
35 | Asphalt paving
36 | Asphalt stripping/signage
37 | Concrete sealing
38 | Concrete coatings/overlays